# Horizon 2020 Project – Kenya Team
## Work Package on Public Health Monitoring
Citizen observations on the impact of use of carbon emission agents arising from use of inefficient combustion device and pesticides on citizen health
### Task
The objective of this work package is to investigate two areas that affect public health through high emission of carbon i.e.:
1. Agrochemicals usage in farming and related activities in rural Kenya.
2. use of inefficient combustion device on citizen health such as bronchitis, lung infections, nasal problems etc. as a result of inhaling carbon fumes emitted by combustion devises
This work package has the aim of establishing the extent of the risk and the areas/population that could be used as test cases in Kenya.
### Input for the tasks
1. Agro-chemicals information sources
2. carbon emitting combustion devices information sources
3. Households using combustion devices and agrochemicals
4. Information from stakeholders such as the Ministry of Health and Ministry of Agriculture,
5. Review of global strategies e.g. MDG for carbon credits
6. Other relevant literature on Carbon Emissions and ratings
### Task description
1. Review of literature
2. Interview with Stakeholders
3. Identification of risk areas and test cases
4. Design of data collection instruments
### Deliverable
1. Report on risk areas and test cases
2. The carbon levels deduced from combustion of carbon fuels by use of household combustion devices is compared to local and global carbon indexes.
3. Data collection instrument
### Deliverable as input
1. Risk areas report for the Risk Literacy-Team
2. Risk areas and test cases for CiObs-Team & Server Infrastructure team
3. Questionnaire for the S/W & Server Infrastructure team
### Project duration
18 months
## Workflow Usability Analysis
### Inputs:
1. The execution of processes that occurs locally using survey instruments like questionnaires, interviews, observations etc.
2. The use of communication tools to conduct the preliminary survey
3. Test cases that will inform us on the population to conduct the preliminary survey
### Task Description/Work Steps:
1. Observe the current workflow in the Kenyan Public Health sector in relation to two aspects;
  1. Agrochemicals in land use.
  2. Carbon emitting energy sources.
2. Conduct usability work analysis
3. Develop optimal work flows
4. Engage relevant stakeholders for feedback on the optimized workflows
5. Monitoring the use of optimized work flows
### Deliverable:
1. Report on optimized work flows
2. Application requirements document
### Deliverables to Other Work Packages:
1. Optimized work flow for the ICT4D and risk literacy team.
2. Applications requirement document for the S/W development and server Infrastructure work packages
### Estimated Duration/Workload:
Three (12) person-month equivalent for development of questionnaires at each iteration;
## Server Infrastructure
In the context of CiObs the Server Infrastructure comprises the hardware, software and networks required to create a system that accepts data sent by citizen observers and providing risk mitigation information as feedback to the citizens.
### Inputs:
This work package requires Citizen Observatory Application System that enables observers to send and receive observed data via multiple channels (input from the Software Development work package).
### Task Description/Work Steps:
1. Acquire two servers and configure them as a cluster with failover for high availability so as to host citizen observatory data. The system will be hosted at the United States International University.
2. Ensure the cluster has sufficient storage capacity for data capture with growth allowance to operate for at least five years.
3. Configure operating systems, fail-over, web server, citizen observatory application system and its database platform, and cloud data backup.
4. Negotiate internet bandwidth and SMS costs with service providers and pay running costs over life span of project.
5. Maintain system licenses for non-open source components over the life span of the project.
6. Monitor and maintain system operations over life span of the project.
### Deliverable/Output:
1. Deliverable1: Configured and operating server cluster with fail over capability. Server hosted at USIU’s demilitarized zone for security purposes.
2. Deliverable2: Configured and operating Citizen Observatory application system.
3. Deliverable3: Citizen Observers sending and receiving Public Health/Land Use Optimization data and information from the server infrastructure.
4. Deliverable4:Monitored and maintained server infrastructure over life span of the project;
### Deliverables to Other Work Packages:
Deliverable1: Reported CiObs data availed to Risk Literacy work package for risk assessment and development of risk mitigation.
### Estimated Duration/Workload:
1. Six (6) person-months for server infrastructure setup;
2. Twenty four (24) person-month equivalent for server infrastructure monitoring and maintenance.
3. Equipment and operating costs include two servers and service provider costs for internet access and SMS costs to ISPs and mobile operators.

## Software Development (Customization & Kiswahili Interface)
The software development component for Kenya involves customization for data correction of Public Health and Land Use Optimization with options for English and Kiswahili interfaces. Some citizen observers in far flung areas of the country may not be conversant in English and hence require a Kiswahili GUI. Hosted on mobile phones, the localized application provides two way communications between the citizen observer as the client and the server at USIU. It enables the observer to report events in their environment or make queries to the server. They will also receive risk mitigation information from the server on the mobile device.

An alternative communication channel will be via a web interface so the Citizen Observers can send and receive information using tablets, laptops and desktop computers.

### Inputs:
1. This work package requires Citizen Observatory Application System hosted at the server (input from the Software Development work package). It also requires inputs from the Usability Workflow Analysis work package.
2. Mobile development environments (IDEs) for common mobile operating systems including Android and windows mobile.
### Task Description/Work Steps:
1. Develop a localized version of the Server application with English and Kiswahili interface processing modules in collaboration with B2M Software AG (Karsruhe).
2. Develop a localized version of the mobile phone client application and provide English and Kiswahili interfaces in collaboration with B2M Software AG (Karsruhe).
3. Develop web enabled server interfaces for client reporting and requests for observers who use tablets, laptops and desktops.
4. Test all applications (server, smart phone, and web apps) for correctness and usability;
5. Update and maintain the applications (both client and server apps) over the lifetime of the project. This involves updating risk mitigation strategies and their accessibility to citizen observers across multiple communication channels.
### Deliverable/Output:
1. Deliverable1: Completed Citizen Observatory server application with English and Kiswahili processing modules.
2. Deliverable2: Completed Citizen Observatory client application with English and Kiswahili GUIs.
3. Deliverable3: Completed Citizen Observatory web application.
### Deliverables to Other Work Packages:
Deliverable1: Reported CiObs data availed to Risk Literacy work package for risk assessment and development of risk mitigation.
### Estimated Duration/Workload:
1. Six (6) person-months for design and development of all three applications (server side, mobile and web access applications);
2. Twenty four (24) person-month equivalent for application systems upgrades; this enables new risk mitigation strategies to be available to citizens.
## Work Package – CiObs
The aim is to provide quantified environmental data products on health and land use at a level that citizen comprehend in a timely manner
### Inputs
Citizen’s observatories call for communities of users that will share:
1. Technological solutions – The citizens own devices will be used to collect data.
2. Information products and services – A state holder analysis will be done by means of implementing living labs in the context of health and land use risk assessment and optimization of resources.
3. Community participatory time and effort – Work flow optimization for citizen observations of health and land use risks and identification of mitigation strategies
### Task Description
1. Preliminary preparation – This calls for the selection of a test region and Identify stakeholders for living labs based on a background review of relevant literature and other sources.
2. Provide user requirements - Effectively gather and feed user requirements to the rest of the project to ensure that the project is user driven.
3. Design data collection instrument – Participate in developing a questionnaire based on user profile, technological abilities, baseline attitudes, and willingness to participate, and contact details.
4. Create awareness - This work package seeks to gain maximum exposure for and raise awareness of the project with all relevant stakeholders, to encourage enthusiastic involvement in the project, and to encourage take up of project deliverables and sustained results during and beyond the project’s life.
5. Data collection- Facilitation of data collection process through testing of dummy data, demonstration of data collection, and error mitigation strategies will be done.
6. Test developed Risk Mitigation strategy – Identification of risks and risk mitigation strategies in both health and land use sectors.
7. Feedback to the user – Evaluate whether the users find the risk mitigation strategies as useful by performing a cost benefit analysis. Establish sustainability of the strategies
### Deliverables
This work package will deliver the common Citizen Observatory environment. This includes:
1. The framework – The test region, and relevant stakeholders for the project.
2. The portal – The data collected will be uploaded onto a portal for ease of access by relevant stakeholders.
3. The documentation- Citizen observatory report
This work package will also address security implications, particularly around personal data, of the Citizen Observatory approach and on the role of authentication and identity.
### Input for other work packages
The framework
The designed framework will be reviewed by the workflow analysis work package to establish how it integrates with other work packages
The portal
- The requirements gathered will be analyzed by the Health and Land use work packages in order to aid in the development of a relevant questionnaire.
- The data collected will be stored in the portal developed by the Software Development and Server Infrastructure work package.
- The data collected will be analyzed in order to identify risk mitigation strategies by the ICT4D work package
### Duration/Workload
24 Months
## Work Package on ICT4D
To implement risk mitigation strategies and identify appropriate communication infrastructure to reach the risk exposed population
### Input for the tasks
1. Risk mitigation strategies from the risk literacy team
2. Communication Infrastructure to disseminate the information
### Task description
1. Identify ICT and Non-ICT communication Infrastructure
2. Disseminate information on risk mitigation strategies
3. To monitor the implementation of the strategies provided
4. Establish the efficacy of the risk mitigation strategies
5. Engagement with the stakeholders
6. Make recommendations for further research
### Deliverable
1. Monitoring and evaluation report
2. Publications on risk awareness strategies
### Deliverable as input
N/A
### Project duration
18 months