Work Package

A work package consists of tasks.

A task, 'Task X' in a work package consists of 5 components (C1-C5):

[C1] INPUT for Task X in a work package - What are the deliverable needs for Task X as INPUT?

[C2] Task DESCRIPTION - What do we perform in Task X?

[C3] DELIVERABLE of Task X - What is the product of Task X?

[C4] DELIVERABLE of the Task X is used as INPUT for e.g. Task Y,Z,...

[C5] Estimated DURATION/WORKLOAD of Task X in person months - Please insert your assumption, a buffer will be added for security reasons (This information is not used explicitly in the 15 pager proposal - just for overall checks for project duration before submission.)

Usability Work-Flow Analysis

A usability evaluation and a work-flow analysis of the ICT and non-ICT (ICT4D after measurement 3) supported communication, of the agro-technical work-flow and of the health-workflow have to be carried out. Thereby, the communication network and the work-flow that is actually transported via communication have to be separated. The execution of certain processes that happen locally is observed. Key questions in this context could be: How can a farm worker perform measurements himself? How does the work-flow of a farm worker or of a health affected person look and what causes concrete actions?

Kenya’s Ministry of Health, produced a whitepaper on Occupational safety and health policy guidelines for the health sector in Kenya in July 2014. The whitepaper identified the healthcare workforce as the most valuable resource in the wake of highly infectious diseases such as Severe Acute Respiratory Syndrome (SARS) and the H1N1 Influenza. The last few months saw the emergence of Ebola in West Africa and the World Bank’s Ebola Impact Index released in October 2014 placed Kenya at position nineteen in the list of countries that were likely to report the first case.
In this work package, our aim will be to optimise the work-flow of Kenyan public health workers in order to apart from ensuring there is as safe a working environment as is practicably possible, meet the requirements for non-transmission of diseases e.g. HIV, Hepatitis B, Hepatitis C etc.
From our observations, we will study the classification of Occupational Safety and Health (OSH) hazards and mitigation in the public health sector in Kenya. These will include but shall not be limited to Biological, Chemical, Physical, Ergonomic, Mechanical and Psychosocial hazards at the workplace that place not just public health workers but patients and the general public at risk.

There is need for systems that support not just data exchange but also the efficacy of addressing medicine calculation issues where contextual information about drug, illness, and patient history are used to reliably inform the prescription process [Okanda, Kanyaru 2014]. Additionally, researchers need to examine how public health information supplied through observatories is contextualized to enable it address four key requirements regardless of the target audience or platform; accuracy, timeliness, relevance and accessibility.
While technology has contributed towards making patient treatment more efficient, existing computer based systems do not provide adequate support for elimination of prescription and dose errors by public health workers or via self-prescription especially in rural areas where according to International Fund for Agricultural Development (IFAD) over 79% of Kenya’s population resides yet very little investment in Internet infrastructure has taken place. In order to address the above four key requirements, we will investigate workflow issues that relate to diagnosis and prescription of medication with the aim of significantly reducing medication errors (which largely occur due to human error).

Work Steps:
[C1] current work-flow in El Salvador (agriculture) and Kenya (health)
[C2] observation of the current workflow and development of a subset of questions 'questions-UWA-0' for the Pretest on the current work-flow in El Salvador (agriculture) and Kenya (health)
[C3] questions-UWA-0'
[C4] provision of these questions to the ICT4D-Team.
[C5] ca. 2 person months
[C1] results of the pretest
[C2] development of 'report-UWA-0' on the current work-flow
[C3] report-UWA-0'
[C4] provision of this report to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team
[C5] ca. 2 person months
[C1] work-flow in the developed risk mitigation strategies
[C2] development of a subset of questions 'questions-UWA-1' for the Measurement 1 on the work-flow in the developed risk mitigation strategies
[C3] 'questions-UWA-1'
[C4] ca. 2 person months
[C5] provision of these questions to the ICT4D-Team
[C1] results of the Measurement 1
[C2] optimisation of the work-flow in the developed risk mitigation strategies based on the results of the Measurement 1.
[C3] optimisation streategies
[C4] ca. 2 person months
[C5] -
[C1] optimisation strategies
[C2] development of the 'report-UWA-1' on the optimised work-flow for the risk mitigation strategies
[C3] 'report-UWA-1'
[C4] ca. 2 person months
[C5] Provision of this report to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team.
[C1] work-flow in the developed risk mitigation strategies after optimisation
[C2] development of a subset of questions 'questions-UWA-2' for the Measurement 2 on the work-flow in the developed risk mitigation strategies
[C3] 'questions-UWA-2'
[C4] ca. 2 person months
[C5] provision of these questions to the ICT4D-Team
[C1] results of the Measurement 2; Prototype 4 of the Software Development Team.
[C2] optimisation of the work-flow in the developed risk mitigation strategies based on the results of the Measurement 2 with inclusion of the developed Prototype 4 of the Software Development Team.
[C3] optimisation streategies
[C4] ca. 2 person months
[C5] -
[C1] optimisation strategies
[C2] development of the 'report-UWA-2' on the optimised work-flow for the risk mitigation strategies
[C3] 'report-UWA-2'
[C4] ca. 2 person months
[C5] Provision of this report to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team.
[C1] work-flow in the developed risk mitigation strategies after optimisation
[C2] development of a subset of questions 'questions-UWA-3' for the Measurement 3 on the work-flow in the developed risk mitigation strategies
[C3] 'questions-UWA-3'
[C4] ca. 2 person months
[C5] provision of these questions to the ICT4D-Team
[C1] results of the Measurement 3; Prototype 4 of the Software Development Team.
[C2] optimisation of the work-flow in the developed risk mitigation strategies based on the results of the Measurement 3 with inclusion of the developed Prototype 4 of the Software Development Team.
[C3] optimisation streategies
[C4] ca. 2 person months
[C5] -
[C1] optimisation strategies
[C2] development of the 'report-RL-UWA-3' on the optimised work-flow for the risk mitigation strategies
[C3] 'report-RL-UWA-3'
[C4] ca. 2 person months
[C5] Provision of this report to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team.