Description of Work Packages

Introduction to Work Packages

The citizen observations are used for risk and resource optimisation in an One Health approach (One Health=Environmental Health + Human Health). Health observations will be evaluated according to the benefit for the environmental health assessment and vice-versa the environmental observations of citizens will be evaluated according to the benefit for the assessment of health risks. The primary driver is a short-term economical benefit that has the potential for a long-term public health improvement. Work packages will measure a change in the work-flow of citizens and detect the workload for an optimised work-flow to assess the sustainability of proposed citizen observatory. A requirement of the combination of work packages is that
- the citizen observations get a short-term (economical) benefit (e.g. precision-farming → less agrochemical with same harvest yield).
- citizens are aware of the long-term benefit of a sustainable citizen observatory (CiOb) (e.g. health related impact of economical benefit and the awareness about the value of citizen observations for a sustainable concept of the CiOb).
- the work-flow for integration of citizen observations will create an acceptable workload for the citizens.
- the whole process of development is citizen-driven/user-driven.
Environmental conditions (e.g. mosquito breeding places, exposure to agrochemicals) induce health risks. The work packages of an integrated approach for One Health uses citizen observations to identify risk mitigation options in the environmental and the health domain, because the health risk can be reduced by intervention for environmental conditions. Furthermore environmental conditions might not be changeable completely and needs additional intervention in the health domain. The citizen observation fulfil two tasks, to collect regional relevant data and an implemented and executed observation plan creates permanent awareness.

ICT4D

To implement risk mitigation strategies, the identification of the ICT and non-ICT communication infrastructure is crucial to reach efficiently risk-exposed population. Therefore, effective non-ICT and ICT-channels will be identified. On this basis, options for optimising the communication channels can be derived by conducting a cost-benefit analysis including the last mile problem. The implementation strategy will be evaluated in pilot regions in rural areas.

Work Steps:
1. Implementation of the Pretest with an existing survey tool: What is currently available for supporting the accessibility of agricultural/health services? Survey on the inventory including the the analysis of the agricultural/health-situation, the ICT-situation, the cultural situation, the socio-economic situation and of a frequently used information and communication-channel. Additionally, the citizen's observations that could be transmitted via the communication channels will be identified. Furthermore, a software analysis will be carried out. Implementing the subsets of questions 'questions-PH-0' from the Public Health Team, 'questions-LUO-0' from the Land Use Optimisation Team, 'questions-RL-0' from the Risk Literacy Team, 'questions-UWA-0' from the Usability Workflow Analysis Team and 'questions-SD-0' from the software development-team.
2. Identification of the existing communication channels and report on how information can be transmitted via the identified communication channels, what information can be transmitted via the identified communication channels, how and what kind of citizen's observations can be transmitted via the communication channels and a classification of the quality of the information transfer via the identified communication channels.
3. Deliverable 1: Provision of the developed 'report-ICT4D-0' to the Risk Literacy-Team.
4. Implementation of the Measurement 1 with an existing survey tool using the identified communication channels based on the results of te prestest. Implementing the subsets of questions 'questions-PH-1' from the Public Health Team, 'questions-LUO-1' from the Land Use Optimisation Team, 'questions-RL-1' from the Risk Literacy Team, 'questions-UWA-1' from the Usability Workflow Analysis Team and 'questions-SD-1' from the software development-team.
5. Optimisation of the existing communication-infrastructure based on the results of the Measurment 1, the'report-RL-1' of the Risk Literacy Team and by implementing the developed Prototype 1 by the Software Development Team.
6. Deliverable 2: Provision of the 'report-ICT4D-1' on the optimised communication-infrastructure to the Risk Literacy-Team and to the Software Development Team.
7. Implementation of the Measurement 2 with an existing survey tool using the identified communication channels based on the results of te prestest. Implementing the subsets of questions 'questions-PH-2' from the Public Health Team, 'questions-LUO-2' from the Land Use Optimisation Team, 'questions-RL-2' from the Risk Literacy Team, 'questions-UWA-2' from the Usability Workflow Analysis Team and 'questions-SD-2' from the software development-team.
8. Optimisation of the existing communication-infrastructure based on the results of the Measurment 2, the 'report-RL-2' of the Risk Literacy Team and by implementing the developed Prototype 4 by the Software Development Team.
9. Deliverable 3: Provision of the 'report-ICT4D-2' on the optimised communication-infrastructure to the Risk Literacy-Team and to the Software Development Team.
10. Implementation of the Measurement 3 with an existing survey tool using the identified communication channels based on the results of te prestest. Implementing the subsets of questions 'questions-PH-3' from the Public Health Team, 'questions-LUO-3' from the Land Use Optimisation Team, 'questions-RL-3' from the Risk Literacy Team, 'questions-UWA-3' from the Usability Workflow Analysis Team and 'questions-SD-3' from the Software Development Team.
11. Optimisation of the existing communication-infrastructure based on the results of the Measurment 3, the 'report-RL-3' of the Risk Literacy Team and by implementing the optomised Prototype 4 by the Software Development Team.
12. Deliverable 4: Provision of the 'report-ICT4D-3' on the optimised communication-infrastructure to the Risk Literacy-Team and to the Software Development Team.

Public Health:

The Public Health Support in rural areas is supposed to be optimised with the present project. In the context of CiObs, the observations of citizens will be used to identify risks or leverage to potential of accessible resources for risk mitigation in the health domain. The risk-exposed citizens receive health risk mitigation support for free. The input data for analysis are a combination of citizen observations and items in a questionnaire. The citizen observation are evaluated according to benefit as permanent sensor for the environmental impact on public health.

Work Steps:
1. Development of a subset of questions 'questions-PH-0' and citizen observations 'CO-PH0' for the Pretest on the topic health and provision of these questions to the ICT4D-Team.
2. Development of a pilot risk mitigation strategy or improvement of existing selected risk mitigation strategies (topic health) based on the results of the Pretest and 'report-UWA-0' of the Usability Workflow Analysis Team.
3. Deliverable 1: Provision of the report-PH-0 on the developed risk mitigation strategies to the Risk Literacy Team and analysis of recommendations, requirements and constraints from the Risk Literacy Team for the further development in the Public Health Team.
4. Development of a subset of questions 'questions-PH-1' for the Measurement 1 on the topic health to determine the impact on health of the developed risk mitigation strategies and provision of these questions to the ICT4D-Team and evaluation of the benefit of citizen observations for the health risk.
5. Optimisation amd implementation of the risk mitigation strategies (topic health) based on the results of the Measurment 1 and the 'report-UWA-1' of the Usability Workflow Analysis Team. Do the citizens regard the risk mitigations strategies as helpful and are they reasonable for integration in their every day workflow?
6. Deliverable 2: Provision of the 'report-PH-1' on the optimised risk mitigation strategies to the Risk Literacy-Team.
7. Analysis of the benefit of enviromental and health related citizen observations (health related observations are indicators for environmental factors of risk). Improve the public health related design of citizen observations and develop a next version of a subset of questions 'questions-PH-2' for the Measurement 2 on the topic health to determine the impact on health of the optimised risk mitigation startegies and provision of these questions to the ICT4D-Team.
8. Optimisation and implementation of the risk mitigation strategies (topic health) based on the results of the Measurment 2 and the 'report-UWA-2' of the Usability Workflow Analysis Team.
9. Deliverable 3: Provision of the report-PH-2 on the developed risk mitigation strategies to the Risk Literacy-Team.
10. Development of a subset of questions 'questions-PH-3' for the Measurement 3 on the topic health to determine the impact on health of the optimised risk mitigation startegies and provision of these questions to the ICT4D-Team.
11. Optimisation of the risk mitigation strategies (topic health) based on the results of the Measurment 3 and the 'report-UWA-3' of the Usability Workflow Analysis Team.
12. Deliverable 4: Provision of the 'report-PH-3' on the developed risk mitigation strategies to the Risk Literacy-Team.

Land Use Optimisation:

The Land Use Optimisation in rural areas is supposed to be optimised with the present project. In the context of CiObs, the observations of citizens have an influence on the agricultural situation. The risk-exposed citizens receive agro-technical benefit (and thus economical benefit) and risk mitigation support for free. The application of agrochemicals is observed. The benefit the user receives for participating in the CiOb is recommendations for improvement of harvest yield.

Work Steps:
1. Development of a subset of questions 'questions-LUO-0' for the Pretest on the topic agriculture and provision of these questions to the ICT4D-Team to determine the currently used technology, methods and awareness of land use.
2. Create a first version of citizen observations that support the detection of awareness, shift in technology use or impact on land use. Development of risk mitigation strategies (topic agriculture) based on the results of the Pretest and 'report-UWA-0' of the Usability Workflow Analysis Team.
3. Deliverable 1: Provision of the 'report-LUO-0' on the developed risk mitigation strategies to the Risk Literacy-Team.
4. Development of a subset of questions 'questions-LUO-1' for the Measurement 1 on the topic agriculture to determine the impact on agriculture of the developed risk mitigation strategies and provision of these questions to the ICT4D-Team.
5. Optimisation of the risk mitigation strategies (topic agriculture) based on the results of the Measurment 1 and the 'report-UWA-1' of the Usability Workflow Analysis Team. Integration of crop health detection (image processing, remote sensing).
6. Deliverable 2: Provision of the 'report-LUO-1' on the optimised risk mitigation strategies to the Risk Literacy-Team.
7. Development of a subset of questions 'questions-LUO-2' for the Measurement 2 on the topic agriculture to determine the impact on agriculture of the optimised risk mitigation startegies and provision of these questions to the ICT4D-Team.
8. Optimisation of the risk mitigation strategies (topic agriculture) based on the results of the Measurment 2 and the 'report-UWA-2' of the Usability Workflow Analysis Team.
9. Deliverable 3: Provision of the 'report-LUO-2' on the developed risk mitigation strategies to the Risk Literacy-Team.
10. Development of a subset of questions 'questions-LUO-3' for the Measurement 3 on the topic agriculture to determine the impact on agriculture of the optimised risk mitigation startegies and provision of these questions to the ICT4D-Team.
11. Optimisation of the risk mitigation strategies (topic agriculture) based on the results of the Measurment 3 and the 'report-UWA-3' of the Usability Workflow Analysis Team.
12. Deliverable 4: Provision of the 'report-LUO-3' on the developed risk mitigation strategies to the Risk Literacy-Team.

Risk Literacy

Risk and resource awareness has to be created for risk mitigation. This can be done via (E-)Learning Modules (ICT for Education - ICT4E) by the education of risk awareness and risk mitigation options.

Work Steps:
1. Development of a subset of questions 'questions-RL-0' for the Pretest on the topic risk literacy and provision of these questions to the ICT4D-Team.
2. Further processing of risk mitigation strategies (topics health & agriculture) based on the results of the Pretest and 'report-UWA-0' of the Usability Workflow Analysis Team. E.g. focus is risk awareness according to existing agro techniques and used agrochemicals or awareness for environmental determinants of health risks (e.g. water bodies as mosquito breading place and trash removal (plastics) as risk mitigation options for reducing the amount of stagnant water as potential breading places).
3. Deliverable 1: Provision of the 'report-UWA-0' on the developed risk mitigation strategies to the Software Development Team.
4. Development of a subset of questions 'questions-RL-1' for the Measurement 1 on the topic risk literacy and provision of these questions to the ICT4D-Team.
5. Optimisation of the risk mitigation strategies (topics health & agriculture) based on the results of the Measurment 1 and the 'report-UWA-1' of the Usability Workflow Analysis Team.
6. Deliverable 2: Provision of the 'report-RL-2' on the optimised risk mitigation strategies to the Software Development Team.
7. Development of a subset of questions 'questions-RL-2' for the Measurement 2 on the topic risk literacy and provision of these questions to the ICT4D-Team.
8. Optimisation of the risk mitigation strategies (topics health & agriculture) based on the results of the Measurment 2 and the 'report-UWA-2' of the Usability Workflow Analysis Team.
9. Deliverable 3: Provision of the 'report-RL-2' on the developed risk mitigation strategies to the Software Development Team.
10. Development of a subset of questions 'questions-RL-3' for the Measurement 3 on the topic risk literacy and provision of these questions to the ICT4D-Team.
11. Optimisation of the risk mitigation strategies (topics health & agriculture) based on the results of the Measurment 3 and the 'report-UWA-3' of the Usability Workflow Analysis Team.
12. Deliverable 4: Provision of the 'report-RL-3' on the developed risk mitigation strategies to the Software Development Team.

Usability Work-Flow Analysis

A usability evaluation and a work-flow analysis of the ICT and non-ICT (ICT4D after measurement 3) supported communication, of the agro-technical work-flow and of the health-workflow have to be carried out. Thereby, the communication network and the work-flow that is actually transported via communication have to be separated. The execution of certain processes that happen locally is observed. Key questions in this context could be: How can a farm worker perform measurements himself? How does the work-flow of a farm worker or of a health affected person look and what causes concrete actions?

Work Steps:
1. Development of a subset of questions 'questions-UWA-0' for the Pretest on the current work-flow in El Salvador (agriculture) and Kenya (health) and provision of these questions to the ICT4D-Team.
2. Deliverable 1: Provision of the 'report-UWA-0' on the current work-flow to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team.
3. Development of a subset of questions 'questions-UWA-1' for the Measurement 1 on the work-flow in the developed risk mitigation strategies and provision of these questions to the ICT4D-Team.
4. Optimisation of the work-flow in the developed risk mitigation strategies based on the results of the Measurement 1.
5. Deliverable 2: Provision of the 'report-UWA-1' on the optimised work-flow for the risk mitigation strategies to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team.
6. Development of a subset of questions 'questions-UWA-2' for the Measurement 2 on the work-flow in the developed risk mitigation strategies and provision of these questions to the ICT4D-Team.
7. Optimisation of the work-flow in the developed risk mitigation strategies based on the results of the Measurement 2 with inclusion of the developed Prototype 4 of the Software Development Team.
8. Deliverable 3: Provision of the 'report-UWA-2' on the optimised work-flow for risk mitigation strategies to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team.
9. Development of a subset of questions 'questions-UWA-3' for the Measurement 3 on the work-flow in the developed risk mitigation strategies and provision of these questions to the ICT4D-Team.
10. Optimisation of the work-flow in the developed risk mitigation strategies based on the results of the Measurement 3 with inclusion of the optimised Prototype 4 of the Software Development Team.
11. Deliverable 4: Provision of the 'report-RL-UWA-3' on the optimised work-flow for risk mitigation strategies to the Public Health Team, the Land Use Optimisation Team and the Risk Literacy Team.
Software Development:

The aim of the present project is the development of a simple, everyday usable open source app for mobile devices, which enables the communication of rare risk-incidents and the access to risk minimising resources. In the context of CiObs, resources and risks can be reported with this app by the citizens. This app should enable to receive risk-related information, to communicate risk-related information and a navigation-function should be available, to navigate a user to safe(r) locations or to risk minimising resources. In this context, the open source app "mixare" could be used as app-client. The design and concept of this App should be similar to "WhatsApp", but independent from "Facebook" or "Google". That is, a GUI similar to the "WhatsApp"-GUI should be used and the messages will not be sent via a server, but as standardised e-mails. Speech recognition is required to simplify data collection within the meaning of the CiOb (especially for users in risk situations or for e.g. illiterate or blind users). The integration to an open source navigation-tool (e.g. Navit) will be crucial to enable navigation. Furthermore, offline use of this app should be enabled, as internet connection is not available everywhere. Multinational standards have to be taken into account (interface to WHO). Keeping an eye on future cellphone generations, the hardware this app will be developed for are cheap smartphones. By setting all these requirements and constraints to soft- and hardware, a potentially large target group is supposed to be reached with this app to be able to having an influence on optimising the health situation. Consequently, the app itself will be open source and thus available free of charge. The decision support data, which is required in developing countries or in locations, where human health is endangered, is freely available. For other users, such decision support data will only be available for a fee, e.g. decision support data for wine growing in Germany, to generate a profit for SMEs. Such decision support data could be information on an optimised way of spraying pesticides (low cost precision farming), which would be used by the wine grower to save costs and to increase sales. The first step would be to develop a first prototype, which enables communication in a simple, everyday usable way. Following this, an encoding-mechanism to protect sensible data should be implemented. Afterward, a link to “mixare” and to an open source navigation system should be realised.
Data Flow:
- Input Client to CiObs-Server:
- MAIN: risk and resource-observations.
- Feedback on regional decision support service provided by SMEs and during the project reported for scientific analysis.
- Quality of regional decision support service provided to SMEs and during the project reported for scientific analysis and work flow optimisation.
- Output CiObs-Server to Client:
- Recommendations for resource allocation and usage of regional resources (e.g. agriculture, precision farming )
- Risk warnings issued by health agencies (with digital signature).
Work Steps:
1. Development of a subset of questions 'questions-SD-0' for the Pretest on usable icons and provision of these questions to the ICT4D-Team.
2. Deliverable 1: Implementation of the developed risk mitigation strategies based on 'report-RL-0' of the Risk Literacy Team and the Pretest.
3. Test-phase of the developed risk mitigation strategies in the CiOb.
4. Development of a subset of questions 'questions-UWA-SD-1' for the Measurement 1 on the work-flow in the developed risk mitigation strategies and provision of these questions to the ICT4D-Team.
5. Deliverable 2: Development of a GUI-Design for a client for spatial decision support via rapid prototyping (Prototype 1) based on the 'report-RL-1' of the Risk Literacy Team and the Pretest.
6. Test-phase of Prototype 1 in the CiOb.
7. Development of a subset of questions 'questions-UWA-SD-2' for the Measurement 2 on the workflow in the developed risk mitigation startegies and provision of these questions to the ICT4D-Team.
8. Deliverable 3: Development of a first prototype of a client for spatial decision support, which enables communication in a simple, everyday usable way, based on the results of Pretest, Measurement 1 and Measurement 2 (Prototype 2).
9. Test-phase of Prototype 2 in the CiOb.
10. Deliverable 4: Implementation of an encoding-mechanism to protect sensible data (Prototype 3).
11. Test-phase of Prototype 3 in the CiOb.
12. Deliverable 5: Realisation of a link to an augmented reality tool (e.g. mixare, TRL 4/5) and to an open source navigation system (e.g. Navit, TRL 6) (Prototype 4).
13. Test-phase of Prototype 4 in the CiOb.
14. Development of a subset of questions 'questions-UWA-SD-3' for the Measurement 3 on the work-flow in the developed risk mitigation strategies and provision of these questions to the ICT4D-Team.
15. Deliverable 6: Optimisation of Prototype 4 based on the results of Measurement 3.

Server Infrastructure

For the software development, an analysis of the existing server infrastructure and the integration of mapping resources in e.g. the App Store/Play Store is important. Low cost Linux-Severs that can be cloned and reproduced free of charge shall be implemented within the CiObs. These servers shall be able to communicate and to network. SMEs shall maintain the distributions and offer services via the network.

Work Steps:
1. The server infrastructure analysis (simultanuously with the Pretest).
2. Deliverable 1: Implementation of the servers (simultanuously with the Pretest).

GIS Mapping

GIS risk and resource mapping is used as back-end for mobile devices. SMEs shall maintain the GIS-data and provide services of an economical benefit of low-cost precision agriculture by integration of citizen observations.

Work Steps:
1. Analysis of the available data in databases like GEOSS and Copernicus Land Monitoring Services.
2. Deliverable 1: Supplement relevant GIS-data to obtain usable GIS-Maps in the context of the CiOb.
3. Provide resulting GIS-Maps to GEOSS and Copernicus Land Monitoring Services (as open content).

Image Processing

Existing image processing technology (multispectral analysis) will be used for crop health, to determine the health status of plants, the fertilizer requirements and the pesticide amount required. Multistructural Analysis is used to determine further actions in the context of precision farming.
Main result: detect environmental conditions that complement citizen observations for economical benefits or health risks, e.g. environmental conditions that trigger communicable diseases or as surveillance mechanism if certain agro-techniques or environmental risk mitigation strategies reported e.g. by citizen observations were successful.

CiObs Implementation

A stakeholder analysis has to be done to be able to implement CiObs by means of implementing Living Labs in the context of Environmental risk assessment and optimisation of resources (e.g. application of agrochemicals), work-flow optimisation for citizen observations of farm workers and environmental risk mitigation strategies; and health risk and resources work-flow for citizen observations and health risk mitigation strategies.

Work Steps:
1. Deliverable 1: Investigation for enabling the selection of an appropriate test region.
2. Deliverable 2: Interdisciplinary analysis of the status quo with the Pretest and identification of Stakeholders for the Living Lab in the context of a CiOb. Determine the first selection of citizen observations that contribute to Environmental Health and/or Public Health.
3. Deliverable 3:Test-phase of the developed risk mitigation strategies. What do the citizens expect as response to the citizen observations? (e.g. improvement of working conditions due to an optimised work-flow.)
4. Deliverable 4: Execution of Measurement 1 in the CiOb. Collect citizen observations and evaluated the contribution to risk assessment and resource awareness.
5. Deliverable 5: Test-phase of Prototype 1 in the CiOb. Last-Mile processing of citizen observations and digital processing of observations.
6. Deliverable 6: Execution of Measurement 2 in the CiOb. Integration of citizen response to provide observations. Do the citizens regard these response as helpful? (short-term and long-term awareness.)
7. Deliverable 7: Test-phase of Prototype 2 in the CiOb. Integration of economical benefit (e.g. low-cost precision agriculture).
8. Deliverable 8: Test-phase of Prototype 3 in the CiOb. Integration of Health Observations as indicators for environmental risks.
9. Deliverable 9: Test-phase of Prototype 4 in the CiOb. Integration of Health Response due to risks induced by environmental conditions.
10. Deliverable 10: Execution of Measurement 2 in the CiOb. Final cost benefit analysis to determine the sustainability of SME services.

Participant No	Participant organisation name	Country	Work package
1 (Coordinator)	University of Koblenz-Landau - Department 7: Natural- and Environmental Sciences (Landau)	Germany	Expertise: Mathematical Modelling, Ecotoxicology, Logistic Optimization, Risk Literacy, AT6FUI: analysis interface requirements & interdisciplinary networking (Health / Environmental Health / UN / WHO) / Usability Workflow Analysis: MAIN Contributor / Risk Literacy: MAIN Contributor / GIS Mapping: MAIN Contributor / Sever Infrastructure / Software Development / CiObs Implementation
2	B2M Software AG (Karlsruhe)	Germany	Expertise: Software Development / Software Development: MAIN Contributor / Risk Literacy (implementation)
3	University of Koblenz-Landau - Department 4: Computer Science (Koblenz)	Germany	Expertise: Image Processing based on Satellite-data, Precision Agriculture / Image Processing: MAIN Contributor
4	Heidelberg University Hospital - Section: Clinical Tropical Medicine (Heidelberg)	Germany	Expertise: Communicable Diseases / Public Health / Risk Literacy
5 ?	German Aerospace Center (DLR) - German Remote Sensing Data Center; Geohazards and Civil Security (Weßling)	Germany	Expertise: Remote Sensing / Software Development
6	Stockholm University - Swedish Programme for ICT in Developing Regions (= SPIDER) (Stockholm)	Sweden	Expertise: ICT4D / ICT4D: MAIN Contributor / Public Health / Usability Workflow Analysis / Risk Literacy
7	Andalusian School of Public Health (Granada)	Spain	Expertise: Public Health in El Salvador / Public Health
8 ?	Edmund Mach Foundation (San Michele all'Adige)	Italy	GIS Mapping
9	Laboratory for Studies of Interactions between Sol-Agrosystem-Hydrosystem, Mixed Unit INRA, SupAgro and IRD (Montpellier)	France	Expertise: Precision Agriculture - Actions concerned to decrease the usage of pesticides by farmers / Land Use Optimisation: MAIN Contributor
10 ?		Denmark	Land Use Optimisation
11	University of El Salvador - Faculty of Natural Science and Mathematics (San Salvador)	El Salvador	Expertise:Surveys in El Salvador, ICT-situation / Server Infrastructure: El Salvador / ICT4D: / Usability Workflow Analysis: / CiObs Implementation: / Investigation for enabling the selection of an appropriate test region
12	National Health Institute of EI Salvador (San Salvador)	El Salvador	Expertise: Health-situation in El Salvador, CKD / Public Health: MAIN Contributor El Salavdor / Server Infrastructure: MAIN Contributor El Salvador / ICT4D / Usability Workflow Analysis / CiObs Implementation
13	United States International University - School of Science and Technology (Nairobi)	Kenya	Expertise: ICT-situation in Kenya / Public Health: MAIN Contributor Kenya / Server Infrastructure:MAIN Contributor Kenya / ICT4D / Usability Workflow Analysis / CiObs Implementation
14	CSIR - Meraka Institute (Pretoria)	South Africa	Expertise: Living Labs / Usability Workflow Analysis / CiObs Implementation: MAIN Contributor
15	Nelson Mandela Metropolitan University, Department of Computing Sciences (Port Elizabeth)	South Africa	Expertise: Data Science, Big Data, Agriculture: green markets / Land Use Optimisation / Software Development / CiObs Implementation